## in
Project_ID | Activity | Category | Planned_Cost | Actual_Cost | Planned_Duration | Actual_Duration | Completion_Percentage | Status | Risk_Level
P001 | Site Preparation | Planning | 50000 | 52000 | 30 | 35 | 10000% | Completed | Medium
P002 | Foundation Work | Construction | 150000 | 165000 | 60 | 70 | 9000% | In Progress | High
P003 | Structural Construction | Construction | 400000 | 385000 | 120 | 110 | 7500% | In Progress | Medium
P004 | Electrical Installation | Installation | 80000 | 0 | 45 | 0 | 0% | Not Started | Low
P005 | Plumbing Installation | Installation | 70000 | 0 | 40 | 0 | 0% | Not Started | Low
P006 | Interior Finishing | Finishing | 200000 | 0 | 90 | 0 | 0% | Not Started | Medium
P007 | Final Inspection | Closing | 30000 | 0 | 15 | 0 | 0% | Not Started | Low